## Estimation
Module | Submodule | Task | Hours
Functional Specification & Requirement Gathering | Requirement Analysis | Document functional specs | 16
Project Management |  | Preparing Project Plan, task list, assignment of tasks, explanation to developers Client communication, project analysis and queries, mid demos to client
Admin | Admin Login | Admin Login | 4
| CMS | Admin should be able to edit all CMS content from AdminPanel | 10
| Projects | Admin should be able to add "Featured Projects" from backend | 10
Admin should be able to add "Work in Progress Projects" from back-end – These projects should not be clickable, only "Featured Projects" should be clickable
|  | Admin should be able to change text, icons and images from backend | 10
| Our Story Manager | Admin can manage the story page contents which will be dynamic | 10
| News Manager | Admin can manage the news | 10
| Testinomials Manager | Admin can manage testinomial to be displayed on front page | 10
| Suscribers | Admin should receive a list of all subscribers in back-end from mailchimp | 10
Frontend | Header | Header should be fixed/sticky when you scroll down | 2
If you click "Norsk" in the header menu, language changes to Norwegian
All the navigation links have different hover color
Please Check "Home – Mobile Version" to see how the menu will be on mobile
| Footer | Where it says "Let's talk Web" The word "Web" should have a dropdown where you can select from "Web", "Mobile", "SEO" & "Hosting". What user has selected should be shown in the email which we receive. The default word will be different from page to page as you can see in the .psd files | 2
|  | You can also click the cross sign on the top right corner to close the contact form. If contact form is closed it should look like the footer on "Contact" .psd. When the contact form is closed you can click "Open form" to open the contact form again | 2
|  | The map should be from Google Maps and not an image | 2
|  | Where it says "Follow us on Facebook" can we add a Facebook like/share API there instead? - Yes | 10
| Home Page | When you are 70% to the bottom a "Go to top" button should pop out from the right side. This goes to all pages | 10
| Our Story Page | Our Story Page | 10
| Projects Page | Display the projects added from backend | 2
| Single Project Page | Display the project details added from backend | 2
|  | If you click "Let's start your project" under "View more projects" you should be redirected to "Contact" page | 10
| News Page | Users should be able to subscribe to newsletter | 2
|  | Is there any module which we can integrate so we are able to send out newsletters from back-end? (MailChimp) | 4
| Single News Page | Single News Page | 10
| Contact Page | There should be Google Maps integrated Submit Contact form and send email | 8
| Multilangual | Multilangual website contents | 50
Testing | Testing | Functionality Testing | 40
Total |  |  | 256
Framework | Laravel | Version 5.1
Language | PHP | Supported By Laravel 5.1
Database | MySql | Supported By Laravel 5.1
Points highlighted as yellow are not making sense for us
Considerations Made
Languages : English & Norwegian
Any changes in above scope will change the esimated hours accordingly
Website features testing will be 20 % of development hours